Dates and duties for (yet to be created) Togiak herring operational plan

Person Date

Aerial surveys Tim/Mariel April/May

AWL sampling (in season and post season) Greg/Katie May-August

In-season news releases Tim April/May

Togiak herring post-season test sampling logistics Tim April/May

Aerial survey biomass calculated Mariel April/May

Aerial survey biomass to biometrics Greg August

Age composition/weight at age to biometrics Greg/Mariel August

ASA model work Sherri, Sara Aug-Nov?

In person mtg to discuss prelim model work (2017 only) Greg, Tim, Sherri, Sara, Jack, Chris Sept?Oct?

Draft model results for biometric review Sherri

Written and oral biometric review Sara, Jane, Chris

Email draft model results to Greg and Tim for review Sherri

Skype walk through with Greg and Tim of model results Sherri

Questions or requested revisions to Sherri Greg, Tim

Final model results in email to Greg and Tim Sherri

Forecast news release draft Greg, (Sherri? Willing if you want my name on there, but not necessary on my account)

Forecast news release review Sherri, Tim, others?

Forecast NR released

Preseason management news release? Tim